## Tasks
Minimum List of Group Project Task |  | EEET2580 Teamwork Contribution Document
You should add more based on your group's work |  | SQUAD [ID] - GROUP [A OR B]
Design ERD |  | Name: Le Trung Kien |  |  | Name: Ung Xuan Dat |  |  | Name: Nguyen Hoang Son |  |  | Name: Chau Tung Nguyen |  |  | Name: Nguyen Tan Phat
Refine ERD |  | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed
MILESTONE 1
Review ERD | ERD Design
Design System Architecture for Level X Requirement RXY
Refine System Architecture for Level X Requirement RXY | Architecture Design
Review System Architecture for Level X Requirement RXY
Design UX/UI for Level X Requirement RXY
Refine UX/UI for Level X Requirement RXY
Review UX/UI for Level X Requirement RXY
HTML/CSS for Level X Requirement RXY
MILESTONE 2
SQL Queries for Level X Requirement RXY | UX / UI Design | Design UX/UI for Home Page | 28/11/2025 | 30/11/2025 | Desgin , review Back-end Architecture | 28/11/2025 | 30/11/2025 | Review UX/UI for Home Page | 28/11/2025 | 30/11/2025 | Review UX/UI for Home Page | 28/11/2025 | 30/11/2025
|  | Design UX/UI for Login Page | 2025-01-12 | 2025-02-12 | Design UI for Admin Login | 2025-01-12 | 2025-02-12 | Review UX/UI for Login Page | 2025-01-12 | 2025-02-12 | Review UX/UI for Login Page | 2025-01-12 | 2025-02-12
Back-end Implementation for Level X Requirement RXY |  | Design UX/UI for Job Search Page | 2025-01-12 | 2025-02-12 | Design UI for Admin DashBoard | 2025-01-12 | 2025-02-12 | Review UX/UI for Job Search Page | 2025-01-12 | 2025-02-12 | Refine UX/UI for Job Search Page | 2025-01-12 | 2025-02-12
|  | Design UX/UI for Subscription Page | 2025-03-12 | 2025-05-12 | Design UI for Job Post | 2025-03-12 | 2025-05-12 | Review UX/UI for Subscription Page | 2025-03-12 | 2025-05-12 | Review UX/UI for Subscription Page | 2025-03-12 | 2025-05-12
Document [R0X] [Diagram/Justification] |  | Design UX/UI for Application Page | 2025-06-12 | 2025-08-12 | Design UI for Application | 2025-06-12 | 2025-08-12 | Review UX/UI for Application Page | 2025-06-12 | 2025-08-12 | Refine UX/UI for Application Page | 2025-06-12 | 2025-08-12
|  | Design UX/UI for Register Page | 2025-09-12 | 2025-10-12 |  | 2025-09-12 | 2025-10-12 | Review UX/UI for Register Page | 2025-09-12 | 2025-10-12 | Review UX/UI for Register Page | 2025-09-12 | 2025-10-12
Refine [R0X] [Diagram/Justification] |  | Design UX/UI for Profile Page | 2025-11-12 | 13/12/2025 |  | 2025-11-12 | 13/12/2025 | Refine UX/UI for Profile Page | 2025-11-12 | 13/12/2025 | Review UX/UI for Profile Page | 2025-11-12 | 13/12/2025
Review [R0X] [Diagram/Justification] | Front-end Development | Front-end Implementation for Level Simplex Requirement 5.1.1 | 2025-05-12 | 2025-08-12 | Intergration Back-end to Front-end for Admin | 2025-05-12 | 2025-08-12 | Front-end Implementation for Level Simplex Requirement 3.1.1 | 2025-03-12 | 2025-05-12 | Front-end Implementation for Level Simplex Requirement 4.1.1 | 2025-05-12 | 2025-08-12
|  | Front-end Implementation for Level Simplex Requirement 5.1.2 | 2025-07-12 | 2025-09-12 | Intergration Back-end to Front-end for Authentication | 2025-07-12 | 2025-09-12 | Front-end Implementation for Level Simplex Requirement 3.1.2 | 2025-08-12 | 2025-10-12 | Front-end Implementation for Level Simplex Requirement 4.1.2 | 2025-07-12 | 2025-09-12
Task of your own choice |  | Front-end Implementation for Level Medium Requirement 5.2.1 | 2025-10-12 | 14/12/2025 | Intergration Back-end to Front-end for Application and Jobpost | 2025-10-12 | 14/12/2025 | Front-end Implementation for Level Medium Requirement 3.2.1 | 15/12/2025 | 17/12/2025 | Front-end Implementation for Level Simplex Requirement 4.1.3 | 2025-10-12 | 14/12/2025
|  | Front-end Implementation for Level Medium Requirement 5.2.2 | 2025-12-12 | 15/12/2025 |  |  |  | Front-end Implementation for Level Medium Requirement 3.2.2 | 20/12/2025 | 22/12/2025 | Front-end Implementation for Level Simplex Requirement 4.1.4 | 2025-12-12 | 15/12/2025
|  | Front-end Implementation for Level Medium Requirement 5.2.3 | 14/12/2025 | 17/12/2025 |  |  |  | Front-end Implementation for Level Ultimo Requirement 3.3.1 | 2026-09-01 | 13/01/2026 | Front-end Implementation for Level Medium Requirement 4.2.1 | 14/12/2025 | 17/12/2025
|  | Front-end Implementation for Level Medium Requirement 5.2.4 | 14/12/2025 | 17/12/2025 | [6 empty] | Front-end Implementation for Level Medium Requirement 4.2.2 | 14/12/2025 | 17/12/2025
|  | Front-end Implementation for Level Ultimo Requirement 5.3.1 | 16/12/2025 | 18/12/2025 | [6 empty] | Front-end Implementation for Level Medium Requirement 4.2.3 | 16/12/2025 | 18/12/2025
[11 empty] | Front-end Implementation for Level Medium Requirement 4.2.4 | 28/11/2025 | 30/11/2025
[11 empty] | Front-end Implementation for Level Medium Requirement 4.2.5 | 30/11/2025 | 2025-01-12
[11 empty] | Front-end Implementation for Level Medium Requirement 4.2.6 | 2025-01-12 | 2025-03-12
[11 empty] | Front-end Implementation for Level Ultimo Requirement 4.2.1 | 2025-02-12 | 2025-04-12
[11 empty] | Front-end Implementation for Level Ultimo Requirement 4.2.2 | 2025-04-12 | 2025-06-12
| Back-end Development | Back-end Implementation for Level Simplex Requirement 5.1.1 | 2026-05-01 | 2026-10-01 | Back-end Implementation for Level Simplex Requirement 1.1.1 | 28/11/2025 | 30/11/2025 | Back-end Implementation for Level Simplex Requirement 3.1.1 | 29/11/2025 | 2025-02-12 | Back-end Implementation for Level Simplex Requirement 4.1.1 | 28/11/2025 | 30/11/2025
|  | Back-end Implementation for Level Simplex Requirement 5.1.2 | 2025-06-12 | 2025-09-12 | Back-end Implementation for Level Simplex Requirement 1.1.2 | 30/11/2025 | 2025-01-12 | Back-end Implementation for Level Simplex Requirement 3.1.2 | 2025-04-12 | 2025-07-12 | Back-end Implementation for Level Simplex Requirement 4.1.2 | 30/11/2025 | 2025-01-12
|  | Back-end Implementation for Level Medium Requirement 5.2.1 | 2025-08-12 | 2025-11-12 | Back-end Implementation for Level Simplex Requirement 1.1.3 | 2025-01-12 | 2025-03-12 | Back-end Implementation for Level Medium Requirement 3.2.1 | 2025-11-12 | 14/12/2025 | Back-end Implementation for Level Simplex Requirement 4.1.3 | 2025-01-12 | 2025-03-12
|  | Back-end Implementation for Level Medium Requirement 5.2.2 | 13/12/2025 | 17/12/2025 | Back-end Implementation for Level Simplex Requirement 1.1.4 | 2025-02-12 | 2025-04-12 | Back-end Implementation for Level Medium Requirement 3.2.2 | 16/12/2025 | 19/12/2025 | Back-end Implementation for Level Simplex Requirement 4.1.4 | 2025-02-12 | 2025-04-12
|  | Back-end Implementation for Level Medium Requirement 5.2.3 | 15/12/2025 | 18/12/2025 | Back-end Implementation for Level Medium Requirement 1.2.1 | 2025-04-12 | 2025-06-12 | Back-end Implementation for Level Ultimo Requirement 3.3.1 | 2026-02-01 | 2026-08-01 | Back-end Implementation for Level Medium Requirement 4.2.1 | 2025-04-12 | 2025-06-12
|  | Back-end Implementation for Level Medium Requirement 5.2.4 | 17/12/2025 | 20/12/2025 | Back-end Implementation for Level Medium Requirement 1.2.2 | 2025-05-12 | 2025-07-12 |  |  |  | Back-end Implementation for Level Medium Requirement 4.2.2 | 2025-05-12 | 2025-07-12
|  | Back-end Implementation for Level Ultimo Requirement 5.3.1 | 19/12/2025 |  | Back-end Implementation for Level Medium Requirement 1.2.3 | 2025-06-12 | 2025-08-12 |  |  |  | Back-end Implementation for Level Medium Requirement 4.2.3 | 2025-06-12 | 2025-08-12
[5 empty] | Back-end Implementation for Level Medium Requirement 1.2.4 | 2025-07-12 | 2025-09-12 |  |  |  | Back-end Implementation for Level Medium Requirement 4.2.4 | 2025-07-12 | 2025-09-12
[5 empty] | Back-end Implementation for Level Ultimo Requirement 1.3.1 | 2025-10-12 | 14/12/2025 |  |  |  | Back-end Implementation for Level Medium Requirement 4.2.5 | 2025-10-12 | 14/12/2025
[5 empty] | Back-end Implementation for Level Ultimo Requirement 1.3.2 | 2025-12-12 | 16/12/2025 |  |  |  | Back-end Implementation for Level Medium Requirement 4.2.6 | 2025-12-12 | 16/12/2025
[5 empty] | Back-end Implementation for Level Simplex Requirement 2.1.1 | 17/12/2025 | 19/12/2025 |  |  |  | Back-end Implementation for Level Ultimo Requirement 4.2.1 | 17/12/2025 | 19/12/2025
[5 empty] | Back-end Implementation for Level Simplex Requirement 2.1.2 | 18/12/2025 | 21/12/2025 |  |  |  | Back-end Implementation for Level Ultimo Requirement 4.2.2 | 18/12/2025 | 21/12/2025
[5 empty] | Back-end Implementation for Level Medium Requirement 2.2.1 | 21/12/2025 | 24/12/2025
[5 empty] | Back-end Implementation for Level Medium Requirement 2.2.2 | 22/12/2025 | 26/12/2025
[5 empty] | Back-end Implementation for Level Ultimo Requirement 2.3.1 | 27/12/2025 | 30/12/2025
[5 empty] | Back-end Implementation for Level Ultimo Requirement 2.3.2 | 29/12/2025 | 2026-02-01
[5 empty] | Back-end Implementation for Level Ultimo Requirement 2.3.3 | 2026-01-01 | 2026-05-01
[5 empty] | Back-end Implementation for Level Simplex Requirement 6.1.1 | 2026-06-01 | 2026-08-01
[5 empty] | Back-end Implementation for Level Simplex Requirement 6.1.2 | 2026-07-01 | 2026-10-01
[5 empty] | Back-end Implementation for Level Medium Requirement 6.2.1 | 2026-09-01 | 13/01/2026
[5 empty] | Back-end Implementation for Level Medium Requirement D.1.1 | 27/12/2025 | 27/12/2025
[5 empty] | Back-end Implementation for Level Medium Requirement D.1.2 | 29/12/2025 | 29/12/2025
[5 empty] | Back-end Implementation for Level Medium Requirement D.2.1 | 2026-01-01 | 2026-01-01
[5 empty] | Back-end Implementation for Level Medium Requirement D.3.1 | 2026-06-01 | 2026-06-01
[5 empty] | Back-end Implementation for Level Medium Requirement D.3.2 | 2026-07-01 | 2026-07-01
[5 empty] | Back-end Implementation for Level Medium Requirement D.3.3 | 2026-09-01 | 2026-09-01

## GitHub Contribution
Ung Xuan Dat
Nguyen Hoang Son
Le Trung Kien
Chau Tung Nguyen